## Sheet1
| Start Date | Completed | Remaining
Initial Research | 2013-01-15 | 30 | 0
Requirements Gatherring | 2013-01-15 | 15 | 0
Planning/Design | 2013-01-21 | 15 | 0
User Interface Prototype | 2013-01-21 | 15 | 0
Location Gathering | 2013-02-10 | 25 | 0
Data Management | 2013-02-25 | 23 | 2
Main Model Class | 2013-02-28 | 30 | 0
Controller (transitions) Development | 2013-02-28 | 34 | 1
UI Enhancements (Visual) | 2013-02-28 | 20 | 10
Ui Critique and Changes | 2013-03-25 | 10 | 20
Testing/Debugging | 2013-03-25 | 0 | 15
Final Test/Debugging/Minor | 2013-03-27 | 0 | 15